## Sheet1
West Nile Virus Challenge
Group 2
Delierables | Predict WNV positive locations - tops 3 "hotspots"
Indentify what weather conditions create ideal conditions for wnv-carrying mosquitos to thrive
Cost/Benefit Analysis of preventative spray vs health costs
Team Member Tasks |  | Week 1 | Week 2: Monday/Tuesday | Wednesday | Thursday | Friday
| All |  |  | check in am | refine presentation | present!
| Mike | intial train EDA, Weather EDA, clean data | Weather visual EDA, shell slide-deck | presentation
| Steve | Train/Test combine and EDA, initial maps, exploring bohek map tools; code combination master | Code combination, split out train & test for modeling | eval models working
| Rajan | Spray data cleaning & EDA; Background & Cost/Benefit Analysis research, explore how can we use Tableau for visualization | synthesizing background research & CBA | presentation
| Laura | Improving Maps, Spray EDA | Visual EDA, maps for presentation; document project management | presentation
Git Workflow | Steve creates master branch
ref Git mini-lesson | When you add code, Checkout master branch |  | git checkout master
| Create new branch to add changes |  | git checkout -b new-branch-describing-work
| When changes complete, remove output |  | Kernel > Restart and clear output
| Add and commit to new branch |  | git add .
git commit -m ""
git push origin new-branch-describing-work
| Intiiate pull request and Steve will merge |  | Pull request on Github